First Unitarian-Universalist Church of Detroit

2016 Strategic Plan – Third Quarter Report Sep 30, 2016

Notes for 2016 Plan

- Responsibility – the assigned person can and should include others in process. This might be a task force, an individual(s), other standing committees, the Board President and/or the Board. The responsible person needs to make it happen, not do it themselves.

- The Plan is our focus/priority for the year – the Church through committees and individuals will do many other things during the year that are not included in the plan, the plan provides our focus for the upcoming year but does not include all activities of the church.

- The Plan can be changed – the future is unknown, our Plan may need to be changed to adapt to a changing environment. The important thing is for everyone to communicate when changes are required.

- The Expected Completion Date – this date indicates the time frame that an action step needs to be completed. It is not a start date. We can celebrate if the action is completed early.

Vision: 	 UU Detroit is an urban center in Detroit for spiritual renewal and social justice.

Mission:  UU Detroit strives to be an expanding transformative community whose mission is to liberate truth, radiate kindness and love courageously.

|  | Strategic Objective & Action Plan | Responsibility | Expected Completion | Quarterly Progress (Completed, Good, Slow, Just Starting, Not achievable) |  |  |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st | 2nd | 3rd | 4th |  |
| GOAL 1 | GOAL 1: Create new opportunities to expand interactions with EMEAC |  |  |  |  |  |  |  |
|  | Objectives and Action Steps |  |  |  |  |  |  |  |
|  | - Under the leadership of our EMEAC Board Representative and Board President, establish a series of meetings with appropriate EMEAC staff and EMEAC Board members to determine areas of mutual interest |  |  |  |  |  |  |  |
|  | ### Begin conversations with EMEAC to determine structure for working relationship | Board President EMEAC Representative | Jan 2016 | S | S | G |  | On 9/7/2016 UU Detroit board met with the EMEAC board to discuss potential common goals |
|  | - Invite EMEAC directors to UU DETROIT Board meeting(s) to present information about EMEAC | Board President EMEAC Representative | Apr 2016 | S | S | S |  | In lieu of inviting the directors to a UU Detroit board meeting; the UU Detroit board met with the EMEAC board on 9/7/2016 to discuss potential common goals |
|  | - Invite EMEAC to develop and provide a joint worship service at UU DETROIT on environmental or social justice issues | EMEAC Representative Worship Committee Chair | Jun 2016 |  | J | G |  | At the UU Detroit board/EMEAC board meeting on 9/7/2016 this was discussed; a subcommittee was formed which will act on the joint worship service |
|  | - Work with EMEAC to determine how UU DETROIT can engage with other Cass Corridor Commons occupants | EMEAC Representative | Dec 2016 | N | J | G |  | At the UU Detroit board/EMEAC board meeting on 9/7/2016 potential common goals were discussed and a subcommittee was formed |

|  | - Integrate EMEAC with First UU Centennial Committee |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Discuss with EMEAC possible Centennial joint activities – include 2-5 options for the discussion | EMEAC Representative Centennial Chair | Dec 2015 | N | N | N |  |  |
|  | - Based on discussion outcome, reach out to other Cass Corridor Commons members for their involvement | EMEAC Representative Board President | Jan 2016 | N | N | N |  |  |
|  | - First Church, EMEAC and Cass Corridor Commons, will strive to publicize one another’s events and activities in their respective newsletters or other publications |  |  |  |  |  |  |  |
|  | - UU Detroit and EMEAC will determine a system to secure information and start publication of EMEAC events/activities | EMEAC Representative Communications Chair | Mar 2016 |  |  |  |  | Not started |
|  | - Using agreed upon system, EMEAC to publicize events | EMEAC Representative | Mar 2016 |  |  |  |  | Not started |
|  | - Promote an inclusive atmosphere within regarding EMEAC/Cass Corridor Commons |  |  |  |  |  |  |  |
|  | - Create and implement a message(s) about EMEAC/Cass Corridor Commons in our Call to Worship or Order of Service – example: “We are a proud member of …,” “We are a supporter of …” | EMEAC Representative Worship Committee Chair | May 2016 | C |  |  |  |  |
| GOAL 2 | GOAL 2: Using the 100th anniversary of the UU sanctuary as a theme, create opportunities to celebrate, increase membership and revenues to connect our past to our future |  |  |  |  |  |  |  |
|  | Objectives and Action Steps |  |  |  |  |  |  |  |
|  | - Create a Centennial Committee to provide leadership of Centennial events |  |  |  |  |  |  |  |
|  | - Recruit committee members from Centennial planning group | Centennial Committee | Dec 2015 | C |  |  |  |  |
|  | - Recruit at Committee Fair | Centennial Committee | Dec 2015 | C |  |  |  |  |
|  | - Recruit volunteers – outside of committee –to support events and preparation of materials | Centennial Committee | Jan 2016 | C |  |  |  |  |
|  | - Define the time frame, theme, activities and materials for Centennial events |  |  |  |  |  |  |  |
|  | - Establish and coordinate with other committees their centennial events and activities | Centennial, Social Justice and Worship Committees Other committees as needed | Jan 15, 2016 | C |  |  |  |  |
|  | - Create and maintain a web-based calendar of centennial events | Centennial and Communication Committees | Jan 15, 2016 | C |  |  |  |  |
|  | - Secure space for events | Centennial Committee | Dec 2015 | C |  |  |  |  |
|  | - Determine cost of events and publicity | Centennial Committee | Jan 2016 | C |  |  |  |  |
|  | - Secure funding to support events and publicity | Centennial Committee | Apr 2016 | N |  |  |  |  |
|  | - Attract participants for events which include current and former members, history buffs, community activists, regional UU members, and others as identified |  |  |  |  |  |  |  |
|  | - Create and distribute written and electronic material to promote events | Centennial and Communication Committees | Mar 15, 2016 | C |  |  |  |  |

|  | - Provide one regional event that involves surrounding UU congregations |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Determine if this event will be separate or part of other events | Centennial Committee | Jan 15, 2015 | C |  |  |  |  |  |
|  | - Determine and invite other congregations to volunteer and participate in event | Centennial Committee | Feb 2016 | C |  |  |  |  |  |
| GOAL 3 | GOAL 3: Create a viable social justice structure built on the 7 principles to sustain our beliefs, outreach efforts and activities |  |  |  |  |  |  |  |  |
|  | Objectives and Action Steps |  |  |  |  |  |  |  |  |
|  | - Secure leadership and members for a social justice committee |  |  |  |  |  |  |  |  |
|  | - Evaluate and select effective leadership structure: committee, task force, team, other | Board President with current Social Justice Committee | Jan 30, 2016 | JS | S | NA |  |  | There is no leadership for the SJ Committee. While individual members continue with SJ activities there is not an active committee to work on objectives. This has been referred to Board to determine action. |
|  | - Based on selected structure, select a co-leader | Board President with current Social Justice Committee | Feb 2016 | JS | S | NA |  |  | See comments in 3.1.a |
|  | - Provide a social justice table at social hour at least monthly for volunteer recruitment and information about social justice issues | Social Justice Committee | Mar 2016 | C |  |  |  |  | See comments in 3.1.a |
|  | - Conduct a conversation with the congregation to determine what social justice means to the church and its members |  |  |  |  |  |  |  |  |
|  | - Develop and provide a social justice history worship service | Social Justice and Worship Committees | Apr 2016 | JS | JS | NA |  |  | See comments in 3.1.a |
|  | - Create a recollection team to prepare community time line, major social justice events/activities and secure speakers | Social Justice Committee | Apr 2016 | JS |  | NA |  |  | See comments in 3.1.a |
|  | - Conduct a congregational conversation day that includes a sermon of reflection / framing, breakout groups during social hour, and a group decision of social justice theme | Social Justice Committee | Jun 2016 | JS |  | NA |  |  | See comments in 3.1.a |
|  | - Create a written social justice plan based on the congregational conversation which will provide structure for the congregation in social justice activities |  |  |  |  |  |  |  |  |
|  | - Select an ad hoc team to create the plan for board approval | Social Justice Committee | Jun 2016 | JS |  | NA |  |  | See comments in 3.1.a |
|  | - Host one social justice event to announce social justice theme and social justice structure | Social Justice Committee | Oct 2016 | JS |  | NA |  |  | See comments in 3.1.a |
|  | - Elevate social justice to a priority at |  |  |  |  |  |  |  |  |
|  | - Create a brief (2 minute) social justice presentation program at least once per month at worship services – these could be personal stories, social justice activities, or other presentation | Social Justice and Worship Committees | Jun 2016 | G | G | NA |  |  | See comments in 3.1.a |
|  | - Determine at least one other ongoing social justice communication for the congregation | Social Justice Committee | Oct 2016 | G |  | NA |  |  | See comments in 3.1.a |

| GOAL 4 | GOAL 4: Develop, conduct and evaluate opportunities and programs for spiritual growth |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Objectives and Action Steps |  |  |  |  |  |  |  |  |
|  | - Begin a congregational conversation of what spirituality means to our church and its members |  |  |  |  |  |  |  |  |
|  | - Explore the possibility of expanding and conducting a two part series “Intro to ” to include “New UU” for new and current members | Minister Membership Committee | Jun 2016 | JS | JS |  |  |  | No 3rd quarterly report. Change in Membership leadership |
|  | - Provide sermon to charge congregation with having ongoing conversation about spirituality for themselves and what this means for spiritual direction of | Minister | Jan 31, 2016 | C |  | G |  |  |  |
|  | - Provide directed conversations with congregation | Minister | May 2016 | JS |  |  |  |  | No 3rd quarter report |
|  | - Determine and recognize certain holidays, high holy days and other important milestones | Minister Worship Committee | May 2016 | JS | G | C |  |  | Survey completed and results will be available in late Oct |
|  | - Based on the spirituality discussion and the 7 Principles, create, provide and evaluate at least 4 spiritual growth programs |  |  |  |  |  |  |  |  |
|  | - Create and provide monthly programs on 7 Principles | Minister | Sep to Dec 2016 |  |  | G |  |  | Started in Oct |
|  | - Create and provide spiritual programs based on spirituality discussion | Minister | Jun to Dec 2016 |  |  |  |  |  | Not started |
|  | - Explore options for monthly group reflections on the sermons – include leadership discussion training and ground rules for discussion | Worship Committee Minister | Sep 2016 | JS | G | C NA |  |  | New Worship leaders have been recruited and trained. Minister has not started group reflections. |
|  | - Provide pre-sermon coffee hours to share ideas about upcoming sermons | Minister | Jan 2016 | JS |  |  |  |  | Not started |
|  | - In cooperation with the Centennial Committee, incorporate the centennial theme into spiritual programs |  |  |  |  |  |  |  |  |
|  | - Meet with Centennial Committee | Minister Worship Committee | Jan 2016 | C |  |  |  |  |  |
|  | - Provide historical services, considering topics such as – How did we evolve from early 20th century into what we are now? How do we imagine a service 100 years from now? | Minister Worship Committee | Apr 2016 | C |  |  |  |  |  |
|  | - Incorporate theme into “UU intro” | Membership Committee | Apr 2016 | G | G | C |  |  |  |